## Sheet1
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
Enoch |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113
Requirements Collection | 2 | 2 | complete | key 1: complete; complete 2: complete
Repo + Git Setup | 1 | 2 | complete | this week 3: complete
Installation | 1 | 1 | complete | planned 4: complete
Player State Machine | 10 | 9 | complete | planned 5: complete; planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete
Movement System | 12 |  | this week | planned 14: this week; planned 15: this week; planned 16: this week; planned 17: this week; planned 18: this week; planned 19: this week; planned 20: this week; planned 21: this week; planned 22: this week; planned 23: this week; planned 24: this week; planned 25: this week
Attack System | 12 |  | this week | planned 14: this week; planned 15: this week; planned 16: this week; planned 17: this week; planned 18: this week; planned 19: this week; planned 20: this week; planned 21: this week; planned 22: this week; planned 23: this week; planned 24: this week; planned 25: this week
Player sprites & animations | 10 |  | planned | planned 26: planned; planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned; planned 31: planned; planned 32: planned; planned 33: planned; planned 34: planned; planned 35: planned
Hit detection & collistion | 10 |  | planned | planned 26: planned; planned 27: planned; planned 28: planned; planned 29: planned; planned 30: planned; planned 31: planned; planned 32: planned; planned 33: planned; planned 34: planned; planned 35: planned
Programming | 12 |  | planned | planned 36: planned; planned 37: planned; planned 38: planned; planned 39: planned; planned 40: planned; planned 41: planned; planned 42: planned; planned 43: planned; planned 44: planned; planned 45: planned; planned 46: planned; planned 47: planned
Testing/Debugging | 8 |  | planned | planned 48: planned; planned 49: planned; planned 50: planned; planned 51: planned; planned 52: planned; planned 53: planned; planned 54: planned; planned 55: planned
Integration | 7 |  | planned | planned 56: planned; planned 57: planned; planned 58: planned; planned 59: planned; planned 60: planned; planned 61: planned; planned 62: planned
Further Testing | 5 |  | planned | planned 63: planned; planned 64: planned; planned 65: planned; planned 66: planned; planned 67: planned
Adding Patterns and Other Requirements | 4 |  | planned | planned 68: planned; planned 69: planned; planned 70: planned; planned 71: planned
totals | 94 | 14
Isaac
Requirements Collection | 2 | 2 | complete | key 1: complete; complete 2: complete
Installation | 1 | 1 | complete | this week 3: complete
Circle Wipe Transition | 2 | 2 | complete | planned 8: complete; planned 9: complete
Stats Screen | 6 |  | planned
Play Button Screen | 4 | 4 | complete | planned 4: complete; planned 5: complete; planned 6: complete; planned 7: complete
You Died Screen | 1 |  | this week | planned 10: this week
You Win Screen | 1 |  | this week | planned 10: this week
Pause Screen | 6 |  | planned | planned 16: planned; planned 17: planned; planned 18: planned; planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned
In Game HUD | 6 |  | this week | planned 10: this week; planned 11: this week; planned 12: this week; planned 13: this week; planned 14: this week; planned 15: this week
Testing | 2 |  | planned | planned 23: planned; planned 24: planned
Integrate With Other Components | 4 |  | planned | planned 25: planned; planned 26: planned; planned 27: planned; planned 28: planned
totals | 35 | 9
Jonathan
Requirements Gathering | 2 | 2 | complete | key 1: complete; complete 2: complete
Research Boss AI Patterns | 4 | 4 | complete | this week 3: complete; planned 4: complete; planned 5: complete; planned 6: complete
Design Boss Behavior Flow | 2 | 2 | complete | this week 3: complete; planned 4: complete
Add Movement Logic | 4 |  | this week | planned 5: this week; planned 6: this week; planned 7: this week; planned 8: this week
Add Detection Logic | 3 |  | this week | planned 5: this week; planned 6: this week; planned 7: this week
Add Attack Logic | 4 |  | this week | planned 5: this week; planned 6: this week; planned 7: this week; planned 8: this week
Implement Exception Handling | 2 |  | planned | planned 9: planned; planned 10: planned
Testing for Each Feature | 3 |  | planned | planned 9: planned; planned 10: planned; planned 11: planned
Integrate Game Engine | 2 |  | planned | planned 12: planned; planned 13: planned
Bug Fixes & Optimization | 2 |  | planned | planned 14: planned; planned 15: planned
Final Testing & Debugging | 2 |  | planned
totals | 30 | 8
Josh
Requirements Gathering | 2 | 2 | complete | key 1: complete; complete 2: complete
Research Enemy AI Patterns | 2 | 2 | complete | this week 3: complete; planned 4: complete
Design Enemy Behavior Flow | 3 | 3 | complete | this week 3: complete; planned 4: complete; planned 5: complete
Create Basic Enemy Framework | 2 | 2 | complete | planned 6: complete; planned 7: complete
Implement Movement Logic | 3 | 3 | complete | planned 8: complete; planned 9: complete; planned 10: complete
Implement Detection Logic | 2 | 2 | this week | planned 8: this week; planned 9: this week
Implement Attack Logic | 3 | 3 | this week | planned 8: this week; planned 9: this week; planned 10: this week
Add Exception Handling | 2 |  | planned | planned 11: planned; planned 12: planned
Unit Testing for Each Feature | 3 |  | planned | planned 11: planned; planned 12: planned; planned 13: planned
Integration with Game Engine | 2 |  | planned | planned 14: planned; planned 15: planned
Bug Fixes & Optimization | 2 |  | planned | planned 16: planned; planned 17: planned
Final Testing & Debugging | 2 |  | planned | planned 18: planned; planned 19: planned
totals | 28 | 17
Keagan
Requirements Collection | 2 | 2 | complete | key 1: complete; complete 2: complete
Installation | 1 | 1 | complete | this week 3: complete
Design Map | 2 | 2 | complete | planned 4: complete; planned 5: complete
Framework for Nodes and Player | 3 | 3 | complete | planned 6: complete; planned 7: complete; planned 8: complete
Assets for Player and Levels/Enemies | 6 | 3 | this week | planned 4: this week; planned 5: this week; planned 6: this week; planned 7: this week; planned 8: this week; planned 9: this week
Develop Transition | 1 |  | this week | planned 6: this week
Add Navigation | 6 |  | planned | planned 10: planned; planned 11: planned; planned 12: planned; planned 13: planned; planned 14: planned; planned 15: planned
Level Loading | 6 |  | planned | planned 7: planned; planned 8: planned; planned 9: planned; planned 10: planned; planned 11: planned; planned 12: planned
Testing | 3 |  | planned | planned 16: planned; planned 17: planned; planned 18: planned
Installation | 1 |  | planned | planned 19: planned
totals | 31 | 11
Miles
Requirements | 1 | 1 | complete | key 1: complete
Data Flow & UI Updates | 2 | 2 | complete | complete 2: complete; this week 3: complete
Design Levels | 3 | 3 | complete | planned 4: complete; planned 5: complete; planned 6: complete
Player Initialization | 2 | 2 | complete | planned 7: complete; planned 8: complete
Enemy Spawning | 3 |  | this week | planned 7: this week; planned 8: this week; planned 9: this week
Environment Setup | 3 |  | this week | planned 7: this week; planned 8: this week; planned 9: this week
UI Integration | 2 |  | planned | planned 7: planned; planned 8: planned
Unit Testing | 3 |  | planned | planned 10: planned; planned 11: planned; planned 12: planned
Integration Testing | 3 |  | planned | planned 13: planned; planned 14: planned; planned 15: planned
Fix Bugs & Optimize | 4 |  | planned | planned 16: planned; planned 17: planned; planned 18: planned; planned 19: planned
Acceptance testing | 2 |  | planned | planned 20: planned; planned 21: planned
Load Level Feature | 4 |  | planned | planned 22: planned; planned 23: planned; planned 24: planned; planned 25: planned
totals | 32 | 8
group totals (hrs) | 250 | 67
group totals ($) | 25000 | 6700